## Sheet1
System Analysis and Design | Unnamed: 1 | Unnamed: 2 | Unnamed: 3 | Unnamed: 4 | Unnamed: 5 | Unnamed: 6 | Unnamed: 7 | Unnamed: 8 | ASSIGNED TO | Unnamed: 10 | START DATE | Unnamed: 12 | END DATE | Unnamed: 14 | STATUS
[11 empty] | 2023-03-01 |  | 2023-04-30 |  | In progress
Conduct user requirements gathering | [10 empty] | 2023-03-02 |  | 2023-04-30 |  | In progress
Analyze user requirements and define use cases | [10 empty] | 2023-03-03 |  | 2023-04-30 |  | In progress
Create system architecture and design documents | [10 empty] | 2023-03-04 |  | 2023-04-30 |  | In progress
Create UI/UX design and wireframes | [10 empty] | 2023-03-05 |  | 2023-04-30 |  | In progress
Define data model and database schema | [10 empty] | 2023-03-06 |  | 2023-04-30 |  | In progress
Front-End Development | [10 empty] | 2023-03-08 |  | 2023-04-30
[11 empty] | 2023-03-09 |  | 2023-04-30 |  | In progress
Implement UI/UX designIN Figma | [10 empty] | 2023-03-10 |  | 2023-04-30 |  | In progress
Develop front-end functionality, including user authentication, user profiles, and tweeting | [10 empty] | 2023-03-11 |  | 2023-04-30 |  | In progress
Integrate front-end with back-end APIs | [10 empty] | 2023-03-12 |  | 2023-04-30 |  | In progress
Back-End Development | [10 empty] | 2023-03-14 |  | 2023-04-30 |  | In progress
[11 empty] | 2023-03-15 |  | 2023-04-30 |  | In progress
Develop back-end functionality, including user management, tweeting, searching, and notifications | [10 empty] | 2023-03-16 |  | 2023-04-30 |  | In progress
Implement database schema and data access layer | [10 empty] | 2023-03-17 |  | 2023-04-30 |  | In progress
Implement RESTful APIs for front-end integration | [10 empty] | 2023-03-18 |  | 2023-04-30 |  | In progress
Implement security measures, including authentication and authorization | [10 empty] | 2023-03-19 |  | 2023-04-30 |  | In progress
Testing and Quality Assurance | [10 empty] | 2023-03-21 |  | 2023-04-30 |  | In progress
[11 empty] | 2023-03-22 |  | 2023-04-30 |  | In progress
Develop test cases and test plans | [10 empty] | 2023-03-23 |  | 2023-04-30 |  | In progress
Conduct unit testing, integration testing, and system testing | [10 empty] | 2023-03-24 |  | 2023-04-30 |  | In progress
Conduct user acceptance testing (UAT) | [10 empty] | 2023-03-25 |  | 2023-04-30 |  | In progress
Conduct performance and load testing | [10 empty] | 2023-03-26 |  | 2023-04-30 |  | In progress
Conduct security testing and vulnerability scanning | [10 empty] | 2023-03-27 |  | 2023-04-30 |  | In progress
Conduct code reviews and quality assurance | [10 empty] | 2023-03-28 |  | 2023-04-30 |  | In progress
Deployment and Maintenance | [10 empty] | 2023-03-30 |  | 2023-04-30 |  | In progress
[11 empty] | 2023-03-31 |  | 2023-04-30 |  | In progress
Deploy the system to production environment | [10 empty] | 2023-04-01 |  | 2023-04-30 |  | In progress
Monitor system performance and availability | [10 empty] | 2023-04-02 |  | 2023-04-30 |  | In progress
Conduct ongoing maintenance and support | [10 empty] | 2023-04-03 |  | 2023-04-30 |  | In progress
Develop new features and enhancements based on user feedback and requirements | [10 empty] | 2023-04-04 |  | 2023-04-30 |  | In progress
Conduct periodic updates and upgrades | [10 empty] | 2023-04-05 |  | 2023-04-30